## Untitled
ID | Asset | Category | Set | New or existing | Used by | Modelling | Texturing | Rig / animation | Wave | Status | Notes
A-001 | SKM_MHC_ValhallaBase (MetaHuman body + face) | Character | Characters | Existing (replaced) | Every player and NPC | MetaHuman Creator in UE 5.8 (MetaHumanCharacter plugin), Optimized / Medium build | MetaHuman skin (baked by the build) | metahuman_base_skel; face mesh follows the body by leader pose | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Replaced the Fable 5.1 organic body with the MetaHuman base MHC_ValhallaBase, nude in underwear, drawn at 122/180.3 scale, facing +Y. Content in /Game/Valhalla/Characters/MetaHuman/ (~455 MB with Build + Export). The Fable body remains as valhalla.Visual.BodyProfile 0. The Paragon Gideon trial body was archived outside the repo (Valhalla-archive/ParagonGideon_2026-09-23). Armour and hair must be rebuilt on metahuman_base_skel (A-002..A-020).
A-002 | SK_Hair_Blonde | Character | Hair | Existing | Players/NPCs | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | Procedural | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Same, shoulder-length strands pick up neck and spine weights. 5,022 tris. /Game/Valhalla/Characters/MetaHuman/Hair/SK_Hair_Blonde; source Import/Characters/MetaHuman/Hair/SK_Hair_Blonde.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Hair for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Clumped hair cards on the new cranium, vertex-colour roots (wave2_hair.py). 5,022 tris. HairStrands procedural set.
A-003 | SK_Hair_Brown_Short | Character | Hair | Existing | Players/NPCs | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | Procedural | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. wave2_hair designs on the MetaHuman cranium (wave2mh_hair.py), pushed clear of the skin, head weights. Vertex colour exported linear. 4,320 tris. /Game/Valhalla/Characters/MetaHuman/Hair/SK_Hair_Brown_Short; source Import/Characters/MetaHuman/Hair/SK_Hair_Brown_Short.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Hair for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Short clumped hair with fringe. 4,590 tris.
A-004 | SK_Hood_Bald_Cap | Character | Hair | Existing | Players/NPCs | Opus 5.5 + Blender MCP | Procedural | Weight transfer from body | Wave 2 | Not needed | Not needed on the MetaHuman (2026-09-23 (Opus 5.5)): the cap was the scalp a hood sat on over the Fable skull; the MetaHuman head is its own scalp, and nothing in code or data references it. The Fable version stays for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Scalp patch on skin material. 972 tris.
A-005 | SK_chest_travelers_jerkin | Equipment | Chest | Existing | leather_tunic | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 leather/cloth | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Torso rings up to the neck, shoulder caps on the MetaHuman arm line, belt, straps and studs. 1,460 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_chest_travelers_jerkin; source Import/Characters/MetaHuman/Equipment/SK_chest_travelers_jerkin.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Leather jerkin with straps, studs, belt. 1,252 tris. ambientCG Leather028.
A-006 | SK_chest_priests_chain | Equipment | Chest | Existing | chainmail | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 metal/chainmail | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Mail shirt and sleeves. Tabard panels draped over the body's outer envelope (so they clear the belly), with a leather hem. 2,104 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_chest_priests_chain; source Import/Characters/MetaHuman/Equipment/SK_chest_priests_chain.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Chain shirt (ambientCG Chainmail004) with cloth tabard. 1,712 tris.
A-007 | SK_chest_apprentice_robe | Equipment | Chest | Existing | cloth_robe | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 cloth | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Robe body and bell sleeves. Skirt draped to the knee over hips and thighs, cream hem, rope belt, cowl. 2,888 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_chest_apprentice_robe; source Import/Characters/MetaHuman/Equipment/SK_chest_apprentice_robe.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Blue robe, bell sleeves, rope belt (ambientCG Fabric032 tinted). 2,488 tris.
A-008 | SK_legs_travelers | Equipment | Legs | Existing | leather_leggings | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 leather/cloth | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Seat and hips as a shell of the body (rings cannot cover the crotch), trouser legs, knee patches, belt. 1,986 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_legs_travelers; source Import/Characters/MetaHuman/Equipment/SK_legs_travelers.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Cloth trousers with leather patches. 1,784 tris.
A-009 | SK_legs_iron_plate | Equipment | Legs | Existing | iron_greaves | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 metal | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Leather breeches shell under a fauld, cuisses, knee cops and greaves. 2,272 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_legs_iron_plate; source Import/Characters/MetaHuman/Equipment/SK_legs_iron_plate.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Plate cuisses/greaves with knee cops (ambientCG Metal009). 1,704 tris.
A-010 | SK_legs_apprentice_robe | Equipment | Legs | Existing | cloth_pants | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 cloth | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Waist band and a skirt draped to the ankle, cream hem. 1,176 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_legs_apprentice_robe; source Import/Characters/MetaHuman/Equipment/SK_legs_apprentice_robe.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Robe skirt (stretches between legs rather than swinging). 1,008 tris.
A-011 | SK_boots_ranger | Equipment | Boots | Existing | leather_boots | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 leather | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. The foot is a shell of the MetaHuman's own foot (toes and all), plus shaft, cuff, instep strap and sole. 2,410 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_boots_ranger; source Import/Characters/MetaHuman/Equipment/SK_boots_ranger.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Leather boots. 1,576 tris.
A-012 | SK_boots_iron_sabatons | Equipment | Boots | Existing | iron_boots | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 metal | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Foot shell in plate, three lames, ankle greave, sole. 2,361 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_boots_iron_sabatons; source Import/Characters/MetaHuman/Equipment/SK_boots_iron_sabatons.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Plate sabatons. 1,528 tris.
A-013 | SK_boots_cloth_slippers | Equipment | Boots | Existing | cloth_sandals | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 cloth | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Foot shell in cloth, ankle tie, thin sole. 1,689 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_boots_cloth_slippers; source Import/Characters/MetaHuman/Equipment/SK_boots_cloth_slippers.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Cloth slippers. 856 tris.
A-014 | SK_gloves_ranger_bracers | Equipment | Gloves | Existing | leather_gloves | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 leather | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. The hand is a shell of the MetaHuman's own hand (five fingers, deforms with the grips). Leather bracers with straps. 2,834 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_gloves_ranger_bracers; source Import/Characters/MetaHuman/Equipment/SK_gloves_ranger_bracers.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Leather bracers. 1,568 tris.
A-015 | SK_gloves_iron_gauntlets | Equipment | Gloves | Existing | iron_gauntlets | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 metal | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Plate hand shell, flared cuff. The Fable knuckle lames were dropped: a band cannot sit on the posed MetaHuman hand. 2,449 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_gloves_iron_gauntlets; source Import/Characters/MetaHuman/Equipment/SK_gloves_iron_gauntlets.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Gauntlets with knuckle lames. 1,424 tris.
A-016 | SK_gloves_cloth_wraps | Equipment | Gloves | Existing | cloth_wraps | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 cloth | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Cloth hand shell and wrapped forearm bands. 2,960 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_gloves_cloth_wraps; source Import/Characters/MetaHuman/Equipment/SK_gloves_cloth_wraps.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Cloth wraps (stacked bands). 1,696 tris.
A-017 | SK_helm_iron_full | Equipment | Helm | Existing | iron_helm | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 metal | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Neck guard, face opening and skull on the MetaHuman head, nasal and brow bars, crest. Rigid on the head bone. 1,016 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_helm_iron_full; source Import/Characters/MetaHuman/Equipment/SK_helm_iron_full.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Full helm, T-visor, crest. 960 tris.
A-018 | SK_hood_scout | Equipment | Helm | Existing | leather_helm | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 leather/cloth | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Hood on the head bone. Leather mantle fitted over the shoulders; it keeps its arm weights so it follows the arms down from the A-pose. 1,324 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_hood_scout; source Import/Characters/MetaHuman/Equipment/SK_hood_scout.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Leather hood with mantle (stiff). 1,140 tris.
A-019 | SK_hat_adept | Equipment | Helm | Existing | cloth_hood | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 cloth | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Brim at the brow, crown, bent cone. Rigid on the head bone. 868 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_hat_adept; source Import/Characters/MetaHuman/Equipment/SK_hat_adept.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Wizard hat with bent cone. 868 tris.
A-020 | SK_cloak_warden | Equipment | Back | Existing | travelers_cloak | Opus 5.5 + Blender MCP: re-fitted to the MetaHuman by script (wave2mh_armour.py / wave2mh_hair.py) | CC0 cloth | Weights transferred from the MetaHuman body/face (metahuman_base_skel), max 6 influences | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Rebuilt for the MetaHuman body. Shoulder cape that follows the arms. Back panel draped to the calf with smoothed spine weights, leather hem, clasp. 888 tris. /Game/Valhalla/Characters/MetaHuman/Equipment/SK_cloak_warden; source Import/Characters/MetaHuman/Equipment/SK_cloak_warden.fbx, Blender assets/Characters/valhalla_mh_equipment.blend. The Fable 5.1 version stays in Characters/Equipment for BodyProfile 0. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Built by wave2_armour.py: ray-cast fitted to the new body, skinned with the body weights, Race_Stocky/Slender keys (not imported: morph targets off). Wool cloak (stiff sheet, no cloth sim). 664 tris.
A-021 | SM_sword_iron | Weapon | Weapons | Existing | iron_sword | Opus 5.5 + Blender MCP: hard-surface model | CC0 metal/leather + baked detail | — | Wave 1 | Done | Done 2026-09-22: Blender (wave1_weapons.py): fullered blade, crossguard, leather grip, pommel. Flat MI_Steel / MI_LeatherWrap. 538 tris.
A-022 | SM_staff_apprentice | Weapon | Weapons | Existing | oak_staff | Opus 5.5 + Blender MCP: organic model | CC0 wood | — | Wave 1 | Done | Done 2026-09-22: Turned shaft with rope grip and bands, three prongs holding a glowing orb (M_OrbGlow). 430 tris.
A-023 | SM_bow_hunting | Weapon | Weapons | Existing | short_bow | Opus 5.5 + Blender MCP: model | CC0 wood/leather | — | Wave 1 | Done | Done 2026-09-22: Recurve limbs, leather grip, string (M_Rope). 156 tris.
A-024 | SM_mace_priests | Weapon | Weapons | Existing | iron_mace | Opus 5.5 + Blender MCP: hard-surface model | CC0 metal | — | Wave 1 | Done | Done 2026-09-22: Flanged head with gold collar and glow core (M_MaceGlow). 552 tris.
A-025 | SM_shield_buckler_iron | Weapon | Shields | Existing | iron_buckler | Opus 5.5 + Blender MCP: hard-surface model | CC0 metal/wood | — | Wave 1 | Done | Done 2026-09-22: Round buckler: iron rim, steel dome, boss, 8 gold studs, strap. 976 tris.
A-026 | SM_shield_kite_iron | Weapon | Shields | Existing | iron_kite_shield | Opus 5.5 + Blender MCP: hard-surface model | CC0 metal/wood + painted heraldry | — | Wave 1 | Done | Done 2026-09-22: Kite shield: oak body, iron rim, blue field (MI_ShieldBlue) with an original gold chevron, boss. 300 tris.
A-027 | SM_dagger_iron | Weapon | Weapons | New | iron_dagger | Opus 5.5 + Blender MCP: hard-surface model | CC0 metal/leather | — | Wave 1 | Done | Done 2026-09-22: New mesh; items.json iron_dagger meshId = dagger_iron. 262 tris. (Earlier note: Today iron_dagger reuses the sword mesh)
A-028 | SM_totem_bone | Weapon | Weapons | New | bone_totem | Opus 5.5 + Blender MCP: organic model | CC0 bone/wood | — | Wave 1 | Done | Done 2026-09-22: New mesh (bone haft, skull knob, tusks, glowing brow gem); items.json bone_totem meshId = totem_bone. 576 tris. (Earlier note: Today bone_totem reuses the mace mesh)
A-029 | Animations: Idle Walk Jog Attack Hit Death (MetaHuman) | Animation | Characters | Existing (replaced) | All characters | — | — | Retargeted from the UE5 Mannequin (IK_Manny -> IK_MH_ValhallaBase) + hand-keyed fixes (Tools/anim_authoring) | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): MetaHuman set in /Game/Valhalla/Characters/MetaHuman/Animations. Idle MH_MM_Idle re-posed relaxed (arms at the sides, hands at rest). Walk MH_MF_Unarmed_Walk_Fwd and Jog MH_MF_Unarmed_Jog_Fwd, play rate matched to speed. Unarmed attack MH_MM_Attack_01. Hit MH_MM_HitReact_Front_Lgt_01 on an additive layer (fixed the combat flicker). Death MH_MM_Death_Front_01. Shoot and Cast moved to A-088/A-091. Mannequin source archived (Valhalla-archive/UE5Mannequins_2026-09-23). Fable 5.1 clips kept for BodyProfile 0.
A-030 | Animations: Run Sit Emotes 2H-attack Block Dodge (MetaHuman) | Animation | Characters | New | All characters | — | — | Hand-keyed (Tools/anim_authoring/author_extra.py): pelvis and planted-foot leg IK added to the author.py engine | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): MH_Sit (0.8 s down to the ground, holds the last frame), MH_Emote_Wave, MH_Emote_Cheer, MH_Emote_Bow, MH_Attack_2H (two-handed overhead chop, left hand on the grip below the right), MH_Block (shield raised to the face, weapon across; the forearm is rolled so the shield faces forward), MH_Dodge (in-place sidestep). Run = MH_MF_Unarmed_Jog_Fwd, already the jog in locomotion. Still NOT wired into gameplay: needs EValhallaAnim entries, /sit and emote commands, a TwoHand weapon style, and Block/Dodge on combat events. ¦ Fable 5.1: Done 2026-09-23 (Fable 5.1): Authored and imported (A_Run, A_Sit, A_Emote_Wave/Cheer/Bow, A_Attack2H, A_Block, A_Dodge); added to character_import.ANIMATIONS. NOT wired into gameplay yet - needs EValhallaAnim entries, run locomotion blend, /sit & emote commands, TwoHand attack cycle, Block/Dodge on combat events.
A-031 | SM_Grass_A / B / C | Environment | Grassland | Existing | L_Grasslands | Ground surface + scatter meshes (Blender MCP) | CC0 tiling material | — | Wave 1 | Done | Done 2026-09-22: Flat tiles, world-aligned CC0 MI_GrassGround (ambientCG Grass004, 140 cm repeat). (Earlier note: Ground reads better as a material than as meshes)
A-032 | SM_Dirt_Straight / Corner | Environment | Grassland | Existing | L_Grasslands | Ground surface + decals | CC0 tiling material | — | Wave 1 | Done | Done 2026-09-22: M_ValhallaGroundBlend: dirt (Poly Haven stony_dirt_path) with a noisy grass verge by vertex colour; road lanes flipped in L_Grasslands so verges face outward (road_lanes.py).
A-033 | SM_Stone_Floor | Environment | Grassland | Existing | L_Grasslands | Ground surface | CC0 tiling material | — | Wave 1 | Done | Done 2026-09-22: MI_StoneFloor (Poly Haven stone_tiles_02), world-aligned 136 cm. Reads a bit bright in full sun - tune BaseColor if needed.
A-034 | SM_Tree_A / B | Environment | Grassland | Existing | L_Grasslands | Opus + Blender MCP: procedural tree (e.g. Blender's Sapling-style generation) + leaf cards | CC0 bark + leaf atlas | Optional wind in Unreal | Wave 1 | Done | Done 2026-09-22: Procedural trunk/limbs (bark: ambientCG Bark012) + canopy clumps: opaque leaf-mass cores + masked two-sided leaf-cluster cards; leaf textures composited from ambientCG LeafSet016 (wave1_leaf_textures.py). New master M_ValhallaFoliage (Two Sided Foliage, edge-on card fade, per-tree tint variation). Old bounds kept. ~2.4k / 1.7k tris, Nanite. No wind yet. (Earlier note: Trees are the hardest environment asset - test early)
A-035 | SM_Rock_A | Environment | Grassland | Existing | L_Grasslands | Opus + Blender MCP: procedural rock | CC0 rock | — | Wave 1 | Done | Done 2026-09-22: Displaced + chiselled boulder, ambientCG Rock030. 662 tris.
A-036 | SM_Water | Environment | Grassland | Existing | L_Grasslands | Unreal water surface | Unreal water material | — | Wave 1 | Done | Done 2026-09-22: Plain 64 cm slab; new master M_ValhallaWater (opaque, glossy, two panning ripple normals, fresnel colour). Ripple normal generated (wave1_water_normal.py). Pond edges still follow the tile grid.
A-037 | VB_StoneWall_Straight / Corner / End | Environment | Grassland | Existing | L_Grasslands | Opus + Blender MCP: procedural modular | CC0 stone | — | Wave 1 | Done | Done 2026-09-22: Rubble courses with footing and coping (MI_StoneWall = Poly Haven castle_wall_slates). Footprint / collision profile unchanged. (Earlier note: Vision blockers: keep footprint and collision exactly)
A-038 | SM_Sand_A / B / C | Environment | Desert | Existing | L_Desert | Ground surface | CC0 tiling material | — | Wave 3 | Not started
A-039 | SM_Dune | Environment | Desert | Existing | L_Desert | Opus + Blender MCP: procedural terrain | CC0 sand | — | Wave 3 | Not started
A-040 | SM_CrackedEarth | Environment | Desert | Existing | L_Desert | Ground surface | CC0 tiling material | — | Wave 3 | Not started
A-041 | SM_Cactus_A / B | Environment | Desert | Existing | L_Desert | Opus + Blender MCP: organic model | Procedural / CC0 | — | Wave 3 | Not started
A-042 | SM_Palm | Environment | Desert | Existing | L_Desert (oasis) | Opus + Blender MCP: procedural tree + frond cards | CC0 bark + leaf atlas | Optional wind | Wave 3 | Not started
A-043 | SM_Boulder_A | Environment | Desert | Existing | L_Desert | Opus + Blender MCP: procedural rock | CC0 sandstone | — | Wave 3 | Not started
A-044 | VB_SandstoneWall_Straight / Corner / End | Environment | Desert | Existing | L_Desert | Opus + Blender MCP: procedural modular | CC0 sandstone | — | Wave 3 | Not started | Vision blockers
A-045 | VB_HouseWall / Door / Window | Environment | Town | Existing | Grasslands town | Opus + Blender MCP: procedural modular timber-frame | CC0 plaster/timber/stone | — | Wave 1 | Done | Done 2026-09-22: Timber frame (plinth, sill, posts, rail, brace) with recessed plaster; window with mullions and shutters; door with plank leaf and iron straps. Bounds unchanged, VisionBlocker kept. (Earlier note: Vision blockers)
A-046 | SM_Roof_Thatch | Environment | Town | Existing | Grasslands town | Opus + Blender MCP: procedural modular | CC0 thatch | — | Wave 1 | Done | Done 2026-09-22: Thick thatch gable with ridge roll, slope-aligned UVs (Poly Haven reed_roof_04). Ridge-roll end cap UVs look stretched close up - minor.
A-047 | SM_Cobble_A / B | Environment | Town | Existing | Grasslands town | Ground surface | CC0 tiling material | — | Wave 1 | Done | Done 2026-09-22: MI_CobbleFloor world-aligned 160 cm (Wave 0 set) applied.
A-048 | SM_WoodFloor | Environment | Town | Existing | Grasslands town | Ground surface | CC0 tiling material | — | Wave 1 | Done | Done 2026-09-22: MI_WoodPlanks (Poly Haven old_wood_floor) world-aligned 204 cm.
A-049 | SM_MarketStall | Prop | Town | Existing | Grasslands town | Opus + Blender MCP: model | CC0 wood/cloth | — | Wave 1 | Done | Done 2026-09-22: Posts, counter, striped awning (MI_CanvasRed / MI_CanvasCream), goods. Footprint kept. 7 material slots (over the 3-slot guide; fine with Nanite, trim sheet later). (Earlier note: Keep footprint (Bjorn stands at it))
A-050 | SM_Well | Prop | Town | Existing | Grasslands town | Opus + Blender MCP: model | CC0 stone/wood | — | Wave 1 | Done | Done 2026-09-22: Stone ring, roof on posts, windlass, rope and bucket. 7 slots (see A-049).
A-051 | SM_LampPost | Prop | Town | Existing | Grasslands town | Opus + Blender MCP: model | CC0 metal/wood | — | Wave 1 | Done | Done 2026-09-22: Iron post and lantern (emissive MI_LanternGlass) + a real warm PointLight per lamp (lamp_lights.py, no shadows).
A-052 | SM_Fence | Prop | Town | Existing | Grasslands town | Opus + Blender MCP: procedural model | CC0 wood | — | Wave 1 | Done | Done 2026-09-22: Picket fence, MI_FenceWood.
A-053 | SM_Signpost | Prop | Town | Existing | Grasslands town | Opus + Blender MCP: model | CC0 wood | — | Wave 1 | Done | Done 2026-09-22: Post and arrow boards.
A-054 | SM_Barrel | Prop | Town | Existing | Grasslands town | Opus + Blender MCP: model | CC0 wood/metal | — | Wave 1 | Done | Done 2026-09-22: Staves and iron hoops (lathe).
A-055 | SM_Crate | Prop | Town | Existing | Grasslands town | Opus + Blender MCP: model | CC0 wood | — | Wave 1 | Done | Done 2026-09-22: Plank crate with corner braces.
A-056 | SM_LootBag | Prop | Gameplay | Existing | Loot bags | Opus + Blender MCP: model | CC0 cloth/leather | — | Wave 1 | Done | Done 2026-09-22: Burlap sack with rope tie (MI_Burlap). Click sphere / collision profile kept. (Earlier note: Keep the click sphere)
A-057 | SM_PortalMarker | Prop | Gameplay | Existing | Portals | Opus + Blender MCP: model + VFX | Procedural | — | Wave 3 | Not started
A-058 | SM_SpawnPad | Prop | Gameplay | Existing | Player starts (editor only) | Leave as is | — | — | — | Not needed | Editor helper
A-059 | Item icons (68) | UI | Icons | Existing | Inventory / action bar / loot | Rendered from the new 3D models in a Blender icon studio | — | — | Wave 4 | Not started
A-060 | Skill icons | UI | Icons | Existing (generated tiles) | Action bar / skills pane | Blender-rendered emblems + painted frames | — | — | Wave 4 | Not started
A-061 | HUD frame art | UI | HUD | New | B-07 Widget Blueprint HUD | Blender-rendered / procedural 2D | CC0 materials | — | Wave 4 | Not started | Pairs with B-07
A-062 | Master PBR materials | Rendering | Materials | New | Everything | Built in Unreal (replaces M_ValhallaToon) | — | — | Wave 0 | Done | Foundation for the remaster look. Done 2026-09-22: M_ValhallaPBR (build_pbr.py) with texture/tint/world-UV/grime/macro-variation params; all 53 M_ValhallaToon instances re-parented (roughness/metallic by family; reparent_to_toon() rolls back). CC0 texture pipeline proven: Poly Haven cobblestone_floor_001 -> MI_CobbleFloor (preview only, applied in Wave 1).
A-063 | Lighting and post (sky / fog / exposure; retire outline) | Rendering | Levels | New | All zones | Built in Unreal | CC0 sky HDRI optional | — | Wave 0 | Done | Done 2026-09-22: lighting_remaster.py LOOK applied to L_World - warm late-afternoon sun, Lumen sky fill + faint cool fill, haze from 1800 cm, gentle grade. Outline retired (valhalla.Visual.Outline 1 restores it). Removed the stray DirectionalLights in L_Grasslands and L_Desert (double shadows).
A-064 | Tavern (exterior + interior kit) | Environment | Town | New | Grasslands town | Opus + Blender MCP: procedural modular | CC0 | — | Wave 5 | Not started | NWN staple
A-065 | Temple / shrine | Environment | Town | New | Grasslands town | Opus + Blender MCP: procedural modular | CC0 | — | Wave 5 | Not started
A-066 | Keep / castle walls and gate | Environment | Town | New | New area | Opus + Blender MCP: procedural modular | CC0 | — | Wave 5 | Not started
A-067 | Ruins set (broken walls / columns / statues) | Environment | Grassland | New | Grasslands and Desert | Opus + Blender MCP: modular + broken variants | CC0 | — | Wave 5 | Not started
A-068 | Bridge and river bank set | Environment | Grassland | New | Grasslands | Opus + Blender MCP: procedural modular | CC0 | — | Wave 5 | Not started
A-069 | Cave kit (walls / ceiling / stalagmites / crystals) | Environment | Cave | New | Greyfell Cave (B-06) | Opus + Blender MCP: procedural rock modular | CC0 rock | — | Wave 5 | Not started | Needed for B-06
A-070 | Dungeon / crypt kit | Environment | Dungeon | New | Future zone | Opus + Blender MCP: procedural modular | CC0 | — | Wave 6 | Not started
A-071 | Interior props (tables / chairs / beds / shelves / books / candles / chests) | Prop | Interiors | New | Tavern / houses | Opus + Blender MCP: models | CC0 | — | Wave 5 | Not started
A-072 | Camp props (tents / campfire / bedrolls / weapon racks) | Prop | Camps | New | NPC camps | Opus + Blender MCP: models | CC0 | — | Wave 5 | Not started | EQ-style camps
A-073 | Foliage variety (bushes / flowers / ferns / dead trees / stumps / logs) | Environment | Grassland | New | Grasslands | Opus + Blender MCP: procedural foliage | CC0 atlases | Optional wind | Wave 5 | Not started
A-074 | Desert variety (bones / skulls / ruins / tents / pottery) | Environment | Desert | New | Desert | Opus + Blender MCP: models | CC0 | — | Wave 5 | Not started
A-075 | Creature: wolf | Creature | Creatures | New | Grasslands enemies | Opus 5.5 + Blender MCP: organic model | CC0 fur/procedural | New quadruped rig + scripted idle/walk/run/attack/hit/death | Wave 6 | Not started | Quadruped animation is the hardest part
A-076 | Creature: giant rat | Creature | Creatures | New | Grasslands enemies (rat_tail drop) | Opus 5.5 + Blender MCP: organic model | Procedural | Quadruped rig (shares wolf rig layout) + scripted anims | Wave 6 | Not started
A-077 | Creature: goblin / kobold | Creature | Creatures | New | Grasslands enemies | Opus 5.5 + Blender MCP: organic model | Procedural / CC0 | Humanoid: SK_Valhalla_Skeleton + shared animations | Wave 6 | Not started | Humanoids reuse the player animations
A-078 | Creature: skeleton warrior | Creature | Creatures | New | Cave / dungeon | Opus 5.5 + Blender MCP: organic model | CC0 bone | Humanoid: SK_Valhalla_Skeleton + shared animations | Wave 6 | Not started
A-079 | Creature: giant spider | Creature | Creatures | New | Cave | Opus 5.5 + Blender MCP: organic model | Procedural | New 8-leg rig + procedural gait animation | Wave 6 | Not started
A-080 | Creature: desert scorpion | Creature | Creatures | New | Desert | Opus 5.5 + Blender MCP: organic model | Procedural | Shares spider rig approach | Wave 6 | Not started
A-081 | Races: elf / dwarf / halfling / half-orc | Character | Characters | Later | Player races | Variants of A-001 on the same skeleton | CC0 / procedural | Shared skeleton + proportion offsets | Later | Deferred | Planned; all characters are human for now. A-001 is designed to allow it ¦ 2026-09-23: on the MetaHuman a race would be another MetaHuman Creator build on metahuman_base_skel; wave2mh_armour/hair re-fit to any body prep() is pointed at.
A-082 | More equipment tiers (steel / mithril / enchanted variants) | Equipment | All slots | New | New items | Opus + Blender MCP: variants of Wave 2 pieces | CC0 + material variants | Weight transfer | Wave 7 | Not started | Driven by new items.json entries
A-083 | Art bible (Docs/ArtBible.md) | Docs | All | New | Every asset | — | — | — | Wave 0 | Done | Scale (122 cm character, 64 cm grid, props ~0.68 x real), palette, material params, texel density and triangle budgets for a mid-range PC (GTX 1660 class), naming, per-asset checklist. Reference images from Kevin go in Docs/reference/ before Wave 2.
A-084 | CC0 texture pipeline (Poly Haven -> Blender -> Unreal) | Tooling | All | New | Every textured asset | Blender MCP (Poly Haven on; Hyper3D/Hunyuan3D/Sketchfab off) | CC0 (Poly Haven, ambientCG) | — | Wave 0 | Done | Blender assets/scripts/valhalla_textures.py exports T_<Set>_BC / _N (DirectX) / _ORM; valhalla_tools/import_texture_sets.py imports and builds MI_<Set> on M_ValhallaPBR.
A-085 | M_ValhallaGroundBlend | Material | Shared | New | Road tiles | Unreal Python (build_pbr.build_ground_blend) | CC0 sets | — | Wave 1 | Done | Done 2026-09-22: Two world-aligned layers blended by vertex colour R with noise-broken edge.
A-086 | M_ValhallaFoliage | Material | Shared | New | Trees (and later bushes) | Unreal Python (build_pbr.build_foliage) | CC0 leaf composites | Optional wind (WPO) later | Wave 1 | Done | Done 2026-09-22: Masked, two-sided, Two Sided Foliage; BaseColor alpha = mask; EdgeFade for cards; per-tree tint from PerInstanceRandom + object-position hash.
A-087 | M_ValhallaWater | Material | Shared | New | SM_Water | Unreal Python (build_pbr.build_water) | Generated ripple normal | — | Wave 1 | Done | Done 2026-09-22: Opaque glossy water, two panning normals, fresnel deep/edge colour.
A-088 | Weapon attacks (MetaHuman): MH_Attack_Sword / _Dagger / _Mace / _Staff / _Bow | Animation | Characters | New | Auto-attack with a weapon (AttackAnimForWeapon, by weaponStyle) | — | — | Hand-keyed in Python (Tools/anim_authoring/author.py) | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): One swing per weapon style: sword slash, dagger thrust, mace overhead, staff two-hand strike, bow draw-and-loose (Shoot). Unarmed stays MH_MM_Attack_01. items.json iron_dagger weaponStyle = dagger.
A-089 | Stance poses: MHP_GripR / MHP_GripL / MHP_ShieldArm | Animation | Characters | New | Any character holding a weapon or shield | — | — | Hand-keyed; layered per branch in ValhallaAnimInstance (HandLayer) | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Fingers close on the weapon in the right hand (or the left for a bow), and the forearm comes up to carry a shield. Blended over idle, walk and attacks. Grip transforms for sword, staff, bow and shield are in ValhallaVisuals GripFrame (Tools/anim_authoring grips).
A-090 | Bow skill hold: MH_Bow_Draw / MH_Bow_Release | Animation | Characters | New | Skills with castAnimation "bow" (ranger_aimed_shot) | — | — | Hand-keyed (author.py) | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Draws the bow and holds at full draw for the cast time, then looses when the cast completes. Skill field castAnimation (skills.json, editor checkbox "Bow Draw While Casting"). Candidates for later: Snipe, Multi-Shot, Serpent Arrow.
A-091 | Casts: MH_Cast_Instant(_Staff), MH_Cast_Channel(_Staff), MH_Cast_Release(_Staff) | Animation | Characters | New | Every spell | — | — | Hand-keyed (author.py) | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Replaced the Gideon cast. Open-hand and staff variants: a looping channel while the cast bar runs, a release when it completes, and an instant cast for spells with no cast time. Works with a mace + buckler.
A-092 | MetaHuman retarget + authoring tools (IK_MH_ValhallaBase, Tools/anim_authoring) | Tooling | Characters | New | Animation pipeline | — | — | IK Rig / IK Retargeter from Python; FK keyframe authoring | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Tools/anim_authoring: skeleton maths, rig, keyframe engine (Catmull-Rom), UE read/write of AnimSequences, retarget script. IK_MH_ValhallaBase is the target rig; run_op_initial_setup is required on every op or the pelvis lands at 0.
A-093 | MetaHuman fitting pipeline (wave2mh_base.py, mh_fbx_export.py, mh_equipment_import.py) | Tooling | Characters | New | Armour and hair for the MetaHuman body | — | — | Weight transfer from the MetaHuman; FBX round trip onto metahuman_base_skel | Wave 2 | Done | Done 2026-09-23 (Opus 5.5): Unreal exports the body and face to Import/Characters/MetaHuman/MH_*.fbx. wave2mh_base.prep() rebuilds them in Blender as the fitting reference and maps Fable landmark heights onto the MetaHuman (Z) and offsets x 180.3/122 (O). drape() hangs cloth over the outer envelope; skin_shell() copies the body's own skin for hands, feet and hips; transfer_weights() takes the MetaHuman's weights. Saved/ClaudeOps/mh_equipment_import.py imports onto metahuman_base_skel and binds MI_ slots by name. The reference pose was checked bone by bone against the body (every skinned bone matches). ValhallaVisuals: SkinnedArtRoot / EquipmentMeshPath / HairMeshPath, and PieceForActiveBody swaps an NPC's Fable piece for its MetaHuman rebuild.